## List1
SEMESTER WEEK
TASK NAME |  | RESPONSIBILITY | LS/SW06 | LS/SW07 | LS/SW08 | LS/SW09 | LS/SW10 | LS/SW11 | LS/SW12 | LS/SW13
Project Initiation | bar: SEMESTER WEEK LS/SW06 to SEMESTER WEEK LS/SW07
| Meeting with the Client | All Implementers | bar: SEMESTER WEEK LS/SW06
| Writing Specifications | D. Macner | bar: SEMESTER WEEK LS/SW06
| Draft Rough Project Plan | D. Hladký | bar: SEMESTER WEEK LS/SW06
| Writing Object Analysis | V. Šedivý | bar: SEMESTER WEEK LS/SW07
| Setting Up the Linux Server | D. Hladký | bar: SEMESTER WEEK LS/SW06 to SEMESTER WEEK LS/SW07
| Familiarization with OPEN UI and Extensions | All Implementers | bar: SEMESTER WEEK LS/SW06 to SEMESTER WEEK LS/SW07
Implementation | bar: SEMESTER WEEK LS/SW08 to SEMESTER WEEK LS/SW13
| Problem Analysis | All Implementers | bar: SEMESTER WEEK LS/SW08
| Solution Design | Y. Kotyk | bar: SEMESTER WEEK LS/SW08
| Web Interface | V. Vladov | bar: SEMESTER WEEK LS/SW08 to SEMESTER WEEK LS/SW09
| Connection to Existing User Database | D. Hladký | bar: SEMESTER WEEK LS/SW08
| Problem Implementation | All Implementers | bar: SEMESTER WEEK LS/SW09 to SEMESTER WEEK LS/SW10
| Creation of the First Prototype | All Implementers | bar: SEMESTER WEEK LS/SW10
Testing | bar: SEMESTER WEEK LS/SW10 to SEMESTER WEEK LS/SW13
| Testing the First Prototype | All Implementers | bar: SEMESTER WEEK LS/SW10 to SEMESTER WEEK LS/SW11
| Creation of the Second Prototype | All Implementers | bar: SEMESTER WEEK LS/SW11
| Testing the Second Prototype | All Implementers | bar: SEMESTER WEEK LS/SW11
| Creation of the Third Prototype | All Implementers | bar: SEMESTER WEEK LS/SW11
| Testing the Third Prototype | All Implementers | bar: SEMESTER WEEK LS/SW11
| Creation of the n-th Prototype | All Implementers | bar: SEMESTER WEEK LS/SW11 to SEMESTER WEEK LS/SW12
| Testing the n-th Prototype | All Implementers | bar: SEMESTER WEEK LS/SW11 to SEMESTER WEEK LS/SW12
Finalization | bar: SEMESTER WEEK LS/SW12 to SEMESTER WEEK LS/SW13
| Test protocol | D. Hladký | bar: SEMESTER WEEK LS/SW12
| Set of Implemented Tests | D. Macner | bar: SEMESTER WEEK LS/SW12
| Project Release | All Implementers | bar: SEMESTER WEEK LS/SW12
| User/Technical Manual | Kotyk, Šedivý, Vladov | bar: SEMESTER WEEK LS/SW12
| Client-Signed Protocol | D. Hladký | bar: SEMESTER WEEK LS/SW13